## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 |  | 2026-01-10 | Login session not persisting | Sprint 1 |  | Functional | Fixed session handling | Week 1 | Closed | Verified
2 |  | 2026-01-19 | Category misclassification | Sprint 2 |  | ML Model | Retrained with better preprocessing | Week 3 | Closed | Accuracy improved
3 |  | 2026-01-21 | Priority override not triggering | Sprint 2 |  | Logic | Added keyword matching | Week 3 | Closed | Tested
4 |  | 2026-01-26 | NER extracting wrong entity | Sprint 3 |  | NLP | Improved training dataset | Week 4 | Closed | Stable
5 |  | 2026-02-12 | Dashboard API returning 401 | Sprint 3 |  | Backend | Fixed authentication middleware | Week 5 | Closed | Working
6 |  | 2026-02-15 | UI alignment issue | Sprint 4 |  | UI | Adjusted CSS styling | Week 6 | Closed | Responsive now

## Sheet2
Logical
User Interface
Maintainability
Standards
Others